## Sheet1
ISMS Implementation Project Plan for DataCore Solutions
ID | Task Name | Duration | Start Date | End Date | Responsibility Party
PHASE 1: INITIATION & PLANNING
1 | Secure Management Commitment | 2 days | 2024-08-01 | 2024-08-02 | CEO
2 | Appoint Project Team | 3 days | 2024-08-05 | 2024-08-07 | CEO, HR Manager
3 | Develop Project Charter | 4 days | 2024-08-08 | 2024-08-11 | Project Manager
4 | Conduct Kick-off Meeting | 1 day | 2024-08-12 | 2024-08-12 | Project Manager
5 | Develop Business Case | 5 days | 2024-08-13 | 2024-08-19 | Project Manager
6 | Cost-Benefit Analysis | 3 days | 2024-08-20 | 2024-08-22 | CFO, Finance Team
7 | Management Approval | 2 days | 2024-08-23 | 2024-08-26 | CEO, Board of Directors
PHASE 2: ISMS ESTABLISHMENT
8 | Define Organizational Boundaries | 3 days | 2024-09-02 | 2024-09-04 | ISMS Steering Committee
9 | Define Information Assets | 4 days | 2024-09-05 | 2024-09-10 | Department Heads, Asset Owners
10 | Document ISMS Scope | 3 days | 2024-09-11 | 2024-09-13 | Project Manager, CISO
11 | Develop Risk Methodology | 4 days | 2024-09-16 | 2024-09-19 | CISO, Security Team
12 | Identify Assets & Risks | 5 days | 2024-09-20 | 2024-09-26 | All Departments, Risk Owners
13 | Risk Analysis & Evaluation | 4 days | 2024-09-27 | 2024-10-02 | CISO, Risk Management Team
14 | Risk Assessment Report | 2 days | 2024-10-03 | 2024-10-04 | Project Manager, CISO
15 | Select Controls | 4 days | 2024-10-07 | 2024-10-10 | CISO, Security Team
16 | Develop Statement of Applicability | 5 days | 2024-10-11 | 2024-10-17 | ISMS Team, CISO
17 | Risk Treatment Plan | 3 days | 2024-10-18 | 2024-10-22 | Project Manager, CISO
PHASE 3: IMPLEMENTATION & OPERATION
18 | Develop ISMS Policy | 5 days | 2024-10-28 | 2024-11-01 | CISO, Top Management
19 | Create Procedures | 10 days | 2024-11-04 | 2024-11-15 | Process Owners, Department Heads
20 | Document Control System | 5 days | 2024-11-18 | 2024-11-22 | QA Manager, Document Controller
21 | Implement Technical Controls | 10 days | 2024-11-25 | 2024-12-06 | IT Manager, Security Team
22 | Implement Physical Controls | 8 days | 2024-12-09 | 2024-12-18 | Facilities Manager, Office Manager
23 | Implement Administrative Controls | 7 days | 2024-12-19 | 2024-12-27 | HR Manager, Department Heads
24 | Develop Training Program | 4 days | 2025-01-06 | 2025-01-09 | HR Manager, CISO
25 | Conduct Organization-wide Training | 6 days | 2025-01-10 | 2025-01-17 | All Employees, Department Heads
PHASE 4: MONITORING & REVIEW
26 | Audit Planning | 3 days | 2025-01-20 | 2025-01-22 | Lead Auditor, Quality Manager
27 | Conduct Internal Audit | 5 days | 2025-01-23 | 2025-01-29 | Internal Audit Team
28 | Audit Report | 2 days | 2025-01-30 | 2025-01-31 | Lead Auditor, Project Manager
29 | Prepare Management Review | 2 days | 2025-02-03 | 2025-02-04 | Project Manager, CISO
30 | Conduct Management Review | 1 day | 2025-02-05 | 2025-02-05 | Top Management, CEO
31 | Address Review Findings | 2 days | 2025-02-06 | 2025-02-07 | Project Team, Department Heads
PHASE 5: CERTIFICATION & IMPROVEMENT
32 | Select Certification Body | 5 days | 2025-02-17 | 2025-02-21 | CEO, Project Sponsor
33 | Stage 1 Audit | 3 days | 2025-02-24 | 2025-02-26 | Certification Body, Project Team
34 | Address Stage 1 Findings | 4 days | 2025-02-27 | 2025-03-04 | Project Team, CISO
35 | Stage 2 Audit | 3 days | 2025-03-05 | 2025-03-07 | Certification Body, Project Team
36 | Implement Corrective Actions | 3 days | 2025-03-10 | 2025-03-12 | Project Team, Process Owners
37 | Project Closure & Handover | 2 days | 2025-03-13 | 2025-03-14 | Project Manager, CISO